## Sheet1
Task Name | September |  |  |  | October |  |  |  | November
| 1-5 | 7 - 13 | 14-20 | 21-27 | 1 - 4 | 5-11 | 12-18 | 19-25 | 26-1 | 2-8 | 9-15
System Draft
(1) Login Interface - Lawas | 1 ✔
(2) Decision Tree Algorithm Integration
(2.1) Import and Preprocess the dataset that will be used for the Algorithm. - Lawas |  | 2.1 ✔
(2.2) Train the Decision Tree model using the training data set - Lawas |  |  | 2.2 ✔
(2.3) Develop API endpoints or services that will use the trained Decision Tree model to process input data and generate predictions - Lawas |  |  |  | 2.3 ✔
(2.4) Verify that the Decision Tree algorithm works as expected within the back-end system. - Lawas |  |  |  | 2.4 ✔
(2.5) Conduct a final review of the algorithm’s integration to ensure all components are functioning correctly - Lawas |  |  |  | 2.5 ✔
(3) Hybrid Method Algorithm Integration
(3.1) Import and Preprocess the data that will be used in the Algorithm - Laserna | 3.1 ✔
(3.2) Train the Hybrid Method model using the training data set - Laserna |  |  |  | 3.2 ✔
(3.3) Develop the collaborative filtering component using user behavior data to identify similar users or items. - Laserna |  |  |  | 3.3 ✔
(3.4) Develop the content-based filtering component using item attributes and user profiles. - Laserna |  |  |  | 3.4 ✔
(3.5) Develop API endpoints or services that utilize the Hybrid Method Algorithm to generate recommendations. - Laserna |  |  |  | 3.5 ✔
(3.6) Verify that the Hybrid Method algorithm works as expected within the back-end system |  |  |  | 3.6 ✔
(3.7) Conduct a final review of the algorithm’s integration to ensure all components are functioning correctly - Laserna |  |  |  | 3.7 ✔
(4) Format the outputs from both algorithms (weaknesses and study recommendations) for display on the front-end. - Dayan |  |  |  |  | 4 ✔
Database Setup
(1) Design and implement the database schema, including tables for users, questions, assessments, and recommendations - Dayan |  |  |  |  | 1 ✔
(2) Define primary and foreign keys to establish relationships between tables - Dayan |  |  |  |  | 2 ✔
(3) Implement encryption for sensitive data fields - Lawas |  |  |  |  | 3 ✔
(4) Define user roles and access permissions within the database -Dayan |  |  |  |  | 4 ✔
(5) Populate the database with initial data sets - Dayan |  |  |  |  | 5 ✔
(6) Ensure that data required by the algorithms is populated and structured correctly - Laserna | [5 empty] | 5-11: 6 ✔
(7) Develop unit tests for each Database - Lawas | [5 empty] | 5-11: 7 ✔
Back-End & Database Integration
(1) Install and configure the necessary database drivers or connectors -Lawas | [5 empty] | 5-11: 1 ✔
(2) Set up and securely store the database connection string, which includes the database host, port, username, password, and database name -Lawas | [5 empty] | 5-11: 2 ✔
(3) Implement error handling mechanisms to manage database- related errors -Lawas | [5 empty] | 5-11: 3 ✔
(4) Develop unit tests for endpoints to verify that they correctly interact with the database and return the expected results -Dayan | [5 empty] | 5-11: 4 ✔
Front-End Development
(1) Define the user flows and key functionalities that need to be accessible through the UI -Dayan | [5 empty] | 12-18: 1 ✔
(2) Create wireframes for the main screens of the application -Dayan | [5 empty] | 12-18: 2 ✔
(3) Implement a component-based architecture to promote reusability and maintainability - Laserna | [5 empty] | 12-18: 3 ✔
(4) Create the layouts for key pages based on the wireframes - Dayan | [5 empty] | 12-18: 4 ✔
(5) Implement user registration, login, and logout functionalities - Laserna | [5 empty] | 12-18: 5 ✔
(6) Implement client-side validation for all forms - Lawas | [5 empty] | 19-25: 6 ✔
(7) Integrate a CSS framework and customize the framework’s theme to match the branding of your application - Lawas | [5 empty] | 19-25: 7 ✔
(8)Prepare the front-end for production deployment by optimizing builds, setting up environment variables, and configuring continuous deployment Pipelines - Dayan | [5 empty] | 19-25: 8 ✔
UI-Back-End Integration
Connect the front- end with the back- end by integrating the APIs developed during the back- end development phase – Laserna & Lawas | bar: November 26-1
Full System Testing
(1) Verify that the Decision Tree algorithm accurately identifies student weaknesses based on assessment results - Lawas | [5 empty] | November 2-8: 1 ✔
(2) Check that the Hybrid Method algorithm generates relevant and personalized study recommendations - Laserna | [5 empty] | November 2-8: 2 ✔
(3) Check that data is correctly stored, retrieved, and updated in the database - Dayan | [5 empty] | November 2-8: 3 ✔
(4) Verify that all navigation paths work correctly and that users can move seamlessly between different parts of the application - Dayan | [5 empty] | November 2-8: 4 ✔
(5) Verify that all forms in the application enforce validation rules both on the client- side and server- side - Laserna | [5 empty] | November 2-8: 5 ✔
(6) Verify that user authentication is secure and that unauthorized access to restricted areas is prevented - Lawas | [5 empty] | November 2-8: 6 ✔
(7) Simulate real- world user scenarios to test the entire application from the perspective of different user Roles - Laserna | [5 empty] | November 2-8: 7 ✔
Debugging & Refinement
After making any updates or changes to the system, test to ensure that previously working features have not been broken – Lawas & Laserna | bar: November 2-8
User Acceptance Testing (UAT)
(1) Conduct comprehensive tests where users perform typical actions within the system - Everyone | [5 empty] | November 9-15: 1 ✔
(2) Conduct performance testing by simulating high user loads and concurrent requests to assess how well the system handles peak usage - Everyone | [5 empty] | November 9-15: 2 ✔
Performance Evaluation
Collect feedback on system performance, including speed, responsiveness, and overall user experience. -Everyone | bar: November 9-15
Final Review
Perform Comprehensive System Walkthrough | bar: November 9-15